## Pre-estimate checklist
Pre-estimate checklist:
Project Process | Yes | No | not necessary
Requirements
Are the Project Requirements clearly documented and Understood? | X
(by both I.S. and the Client?)
Is the criteria for meeting each requirement defined? | X
Are the Project Requirements Baselined (Under change control)? | X
Is there a "Client approved" plan for Requirements changes? | X
Has a Requirements Traceability Matrix been developed? | X
Have the requirements been validated against the business objectives? | X
Have you considered all of the processes that must be followed during | X
the project life cycle?
Have you considered all of the interfaces that must be adhered to? | X
Scoping
Has a Statement of Work (SOW) been reviewed/approved by the Client | X
Has the Statement of Work been reviewed by the virtual | X
team partners?
Has a Work Breakdown Structure (WBS) been reviewed by the Client | X
Has the WBS been reviewed by the virtual team partners? | X
Risk
Has a formal Risk Assessment been done? | X
(including probability, impacts, avoidance & recovery)
Is there an approved Risk Management Plan? | X
Was a Client representative involved with the Risk Management Plan? | X
Were appropriate I.S. resources involved in the Risk Management Plan? | X
Environments
Is the process for identifying, acquiring, establishing, and verifying the | X
environment understood and included in the plans for the project?
Is the Development environment adequate to support the project? | X
Is the Operational environment adequate to support the project? | X
Staff
Are appropriate staff available for the project? | X
Are the resources committed to participate in the required activities? | X
Is there a training plan to cover deficiencies? | X

## (1) Estimate summary
Department name |  |  | Project name/Number
Project Manager Name, PM |  |  | Date
| Effort | 3300
| Hardware | 7200
| Software | 6800
| NetWorks | 1330
| On-going support | 1800
| Admin costs not in overhead | 1000
| Sub Total | 21430
| Risk | 2143 |  | Project Risk Factor | 10%
| Change | 642.9 |  | Project Change Factor | 3%
| Total (includes Risk & Change) | 24215.9

## (2) Effort
Total "Effort estimate" |  |  | 3300
Project Name/Number ______________ | [7 empty] | Project Manager __________
Date __________
Project Activity/Task ID (#) |  | Project Activity/Task name/description | Resource type | Resource Quantity (by type) * | rate per hour | Effort hours required | estimated effort cost (sub total) | Remarks
|  | documentation (summary plan) |  | 1 |  |  | 500
|  | Project Development Phase |  | 1 |  |  | 1000
|  | detailed project document |  |  |  |  | 300
|  | completed work |  | 1 |  |  | 1500
[6 empty] | Total | 3300
|  | Resource type | estimated | not estimated * |  | Resource type estimate checklist:
IS Project Team
|  | Project Manager |  | X
|  | Project Leader |  | X
|  | Analyst | X
|  | Programmer |  | X
|  | Tester | X
|  | Documentation |  | X
|  | Third Party Prime (e.g. EPIC, Origin, BaaN) |  | X
|  | BaaN Core Program Interface Prime |  | X
|  | Integration Partners Core |  | X
|  | Integration Partner Non-Core |  | X
IS Support Functions
|  | New Product Introduction (NPI) Prime |  | X
|  | DBA |  | X
|  | Processing Services Prime |  | X
|  | Desktop Prime |  | X
|  | Networking Services Prime |  | X
|  | Vendor Management Prime |  | X
|  | Deployment Prime |  | X
|  | Captive Office Prime |  | X
|  | Functional Design Expert |  | X
|  | Detail Design Expert |  | X
IS Other
|  | Configuration Management Prime |  | X
|  | Client Manager |  | X
|  | Internal Audit | X
|  | Quality Assurance Prime |  | X
|  | Product Prime |  | X
|  | Program Office Prime |  | X
|  | Release Manager |  | X
Client
|  | Client Prime |  | X
|  | DEM Prime |  | X
|  | Process Prime |  | X
|  | Indirect |  |  |  | Indirect estimate checklist:
| Subject Matter Experts from Client Organizations |  |  | X
| Subject Matter Experts from other IS depts. |  |  | X
| Employee Advisory Committees |  |  | X
| Client Advisory Committee |  |  | X
| Vendor Management |  |  | X
Userid Administration
| Data Standards Forum |  |  | X
| Data Management |  |  | X
| Architecture |  |  | X
| Core Baan Program interface organization |  |  | X
| Integration Testing |  |  | X
| Item |  | estimated | not estimated * |  | Project support estimate checklist:
| Database Administration |  |  | X
| Resource Management |  |  | X
| Verification and Validation |  |  | X
| Configuration Management |  |  | X
| Quality Assurance/Facilitation |  |  | X
| Electronic Data Interchange |  |  | X
| New Product Introduction |  |  | X
| Product Management |  |  | X
| Core Baan Program Interfaces |  |  | X
| Networking and Computing |  |  | X
| Processing Services |  |  | X
| Finance |  |  | X
| Application Modifications - vendor |  |  | X
| Third Party Suppliers(e.g. EPIC, Baan, Origin) |  |  | X
| IS Skills Development |  |  | X
| 3rd party warranty support vs contracted support. |  |  | X
| computer operations support |  |  | X
| outsourced support |  |  | X
| Level-1/Level-2 support |  |  | X

## (3) Hardware
Total "Hardware Cost estimate" |  |  |  |  | 7200
Sample table
| Server Hardware … | Price per unit | Quantity | Total |  | Supporting information
| for development | 500 | 1 | 500
| for test | 300 | 2 | 600
| for training | 900 | 1 | 900
| for production | 400 | 2 | 800
| Total (Server) |  |  | 2800
| Desktop Hardware … | Price per unit | Quantity | Total |  | Supporting information
| for development | 500 | 3 | 1500
| for test | 150 | 2 | 300
| for training | 200 | 5 | 1000
| for production | 200 | 8 | 1600
| Total (Server) |  |  | 4400
7200
Hardware estimate checklist:
| Item |  | estimated | not estimated *
| Cpu Hardware |  | X
| Servers |  | X
| Modem |  |  | X
| Extraordinary power supply |  |  | X
needs
| Backup Systems |  |  | X
| Disaster Recovery Systems |  |  | X
| Additional Memory |  |  | X
| Processing Services |  |  | X
| Disk Storage |  |  | X
| Tape Backup |  |  | X
| UPS |  |  | X
| Switching devices |  |  | X
| Routers |  |  | X
| Racks |  |  | X
| Local taxes |  |  | X
| shipping, handling(delivery) |  |  | X
| installation |  |  | X

## (4) Software
Total "Software Cost estimate" |  |  |  | 6800
Sample table
| Server Software … | Price per unit | Quantity | Total | Supporting information
| for development | 300 | 2 | 600 |  | NetBeans, Microsoft Office
| for test | 400 | 2 | 800
| for training | 400 | 5 | 2000
| for production | 400 | 5 | 2000
| Total (Server) |  |  | 5400
| Desktop Software … | Price per unit | Quantity | Total | Supporting information
| for development | 200 | 1 | 200
| for test | 200 | 1 | 200
| for training | 200 | 2 | 400
| for production | 200 | 3 | 600
| Total (Server) |  |  | 1400
6800
Software estimate checklist:
| Item | estimated | not estimated *
| Application Licenses | X
| Security (Nortel.Access) |  | X
| RDBMS Licences |  | X
| Project specific Software tools |  | X
| Application Mods - vendor |  | X
| Any costs that this project must bear |  | X
to decommission Legacy Systems
| Archiving |  | X
| Communication SW (e.g. MQ Series) |  | X
| Userid Administration |  | X
| also include: |  | X
| The number of licenses | X
| Any installation costs | X
| S&H costs |  | X
| support costs |  | X

## (5) Network HW-SW
Total "Network Cost estimate" |  |  |  | 1330
| Server Network needs … | Price per unit | Quantity | Total |  | Supporting information
| for development | 100 | 1 | 100
| for test | 100 | 1 | 100
| for training | 100 | 1 | 100
| for production | 200 | 2 | 400
| Total (Server) |  |  | 700
| Desktop Network needs … | Price per unit | Quantity | Total |  | Supporting information
| for development | 90 | 1 | 90
| for test | 90 | 1 | 90
| for training | 90 | 1 | 90
| for production | 180 | 2 | 360
| Total (Server) |  |  | 630
1330
Network estimate checklist:
| Item |  |  |  | estimated | not estimated *
| LAN |  |  |  | X
| WAN |  |  |  | X
| Routers |  |  |  |  | X
| Dial-up Lines |  |  |  |  | X
| Dedicated lines |  |  |  |  | X
| Satellite |  |  |  |  | X
| Ports |  |  |  |  | X
| Phones |  |  |  |  | X
| Controllers |  |  |  |  | X
| Switches |  |  |  |  | X
| SW licenses |  |  |  |  | X
| Setting up Access (e.g. Secure ID) |  |  |  |  | X
| Other security … Firewall, etc. |  |  |  | X
Processing Services
| (estimate 15-20% of the hardware costs per annum) |  |  |  |  | X

## (6) On-Going Support
Total "On-going support estimate"
| On-Going support items |  |  | 2 | Supporting information
| Disaster Recovery |  |  |  | 800
| Depreciation costs |  |  |  | 1000
1800
"On-going" support estimate checklist:
| Item |  |  | estimated | not estimated *
Level-1/L-2 support (Level of service - Platinum, Gold, Silver, Bronze)
| New user setup |  |  |  | X
| Password/User ID restores |  |  |  | X
| Archiving of data |  |  | X
| Emergency Recovery |  |  |  | X
| Data integrity issues |  |  |  | X
| Regular Job scheduling |  |  | X
| Ad-hoc production job scheduling requests |  |  |  | X
| Report generation & Elimination |  |  | X
| Procedures Clarification |  |  |  | X
| Ticket Status Updates |  |  |  | X
| Scheduled maintenance |  |  |  | X
| Recovery from failed job |  |  |  | X
| Information flow monitoring |  |  |  | X
| Standard Backups (non-Mac or PC) |  |  |  | X
| System Availability Monitoring & Correction |  |  |  | X
| System Recovery |  |  |  | X
| Disk space management (non-Mac or PC) |  |  |  | X
| Basis Security Services and Precautions |  |  |  | X
| Root Cause Analysis |  |  |  | X
| Problem Resolution |  |  |  | X
| Liason with DBA, Networks, Local I/S |  |  |  | X
| Patch Maintenance |  |  | X
| Time Zone Coverage |  |  |  | X
| Multiple Site Support |  |  |  | X
| Client - Support Communication |  |  |  | X
| Site to Site Communication |  |  |  | X
Level - 3 Support (above items plus):
| Bug fixes |  |  |  | X
| Test Environment Costs |  |  |  | X
Pre-Implementation Support:
| Product Support during SIT/BIT/NIT Testing |  |  |  | X
Release Strategy Support:
| Bug and Enhancements |  |  | X | X
| Implementation |  |  | X | X
| Customization |  |  |  | X
"On-going" support estimate checklist: (cont'd)
| Item |  |  | estimated | not estimated *
GES Renderings:
| Job scheduling |  |  |  | X
| Scheduled maintenance |  |  |  | X
| Standard Backups (non-Mac or PC) |  |  | X
| System Availability Monitoring & Correction |  |  | X
| OS Patch Maintenance |  |  |  | X
DBA:
| Back-up |  |  |  | X
| Scheduled maintenance |  |  |  | X
| DB Availability Monitoring & Correction |  |  |  | X
| DB Patch Maintenance |  |  |  | X
Network management:
| Back-up |  |  | X
| Scheduled maintenance |  |  | X
| NW Availability Monitoring & Correction |  |  |  | X
| NW Patch Maintenance |  |  |  | X
Hardware, Storage (DASD), etc. (requirements for near & long-term)
Lease Penalties
Disaster Recovery
Depreciation costs

## (7) Admin costs not in overhead
Total estimate for |  |  | 1000
Admin costs not in overhead
Sample table
| Admin items |  |  | Supporting information
Travel
| Facilities(real estate) |  |  | lab | rm1000
etc.
1000
"Admin costs not in Overhead" estimate checklist:
| Item |  | estimated | not estimated *
| Conferences |  |  | X
| Internal or external |  |  | X
| Face to Face meetings |  | X
| Audio/Video teleconferences |  |  | X
| Internal Audit |  |  | X
Quality Assurance
| extraordinary Communications |  |  | X
| Printing (e.g. manuals, training material) |  | X
| Project Website development and maintenance |  | X
| Use of Learning Institute |  |  | X
| Administration support |  |  | X
| Marketing |  |  | X
| Electrical work |  |  | X
| network connections |  |  | X
| lighting |  |  | X
| furniture |  |  | X
| special Air conditioning |  |  | X
| Team recognition/celebration |  |  | X

## Risk & Change
project risk chart
analysis and documentation of project risks:
|  | Probability of Occurrence |  |  | Impact |  |  | Planned Action
Risk number | Activity/Requirement | low | medium | high | low | medium | high | no action | type of action | Risk weight *
1 | Contract Termination | x |  |  |  | x |  |  | Accept | 50
2 | Implementation Issues | x |  |  |  |  | x |  | Prevent | 40
3 | User Acceptance | x |  |  |  |  | x |  | Prevent | 60
4 | Missed Deadline | x |  |  | x |  |  |  | Prevent | 45